## Sheet1
The Children's Authority of Trinidad and Tobago
Planned Procurement Schedule 2023-2024
NO | Project Number | Project Name | UNSPSC Code Lvl 3 | Brief Description | Proposed date for Issue of Bidding Documents | Expected Delivery/Completion Date | Estimated Project Duration (For works & Services | Procurement Method | Standstill Period (If Applicable ) - No of Days | Contract Type
1 |  | Santa Cruz CSC Building No1 Work Package No2 |  | Enhancement of security infrastructure at the facility, aligned with TTPS, TTFS & Public Health recommendations | 2023-11-30 | 2024-03-30 | 3 months | Competitive Bidding |  | CATT SFC
2 |  | Establishment of a Child Support Centre in Tobago |  | Refurbishment & Outfitting of facility for Children in Need of Supervision | 2023-12-15 | 2024-04-30 | 4 months | Competitive Bidding |  | CATT SFC
3 |  | Establishment of a Child Support Centre in Tobago |  | Construction of purpose built facility for Children in need of Care & Protection | 2023-12-15 | 2024-02-28 | 2 months | Competitive Bidding |  | CATT SFC
4 |  | Furniture, Fixtures & Equipment for the CSC Facility (Port Of Spain/North) |  | Outfitting of Client Centre Port of Spain | 2023-12-12 | 2024-02-28 | 2 months | Competitive Bidding |  | CATT SFC
5 |  | Furniture, Fixtures & Equipment for the National Care & Empowerment Centre (South) |  | Outfitting of the National Care & Empowerment Centre | 2023-12-22 | 2024-05-12 | 6 months | Competitive Bidding |  | FIDIC Red Book
6 |  | National Care and Empowerment Centre (Phase 2) |  | Construction of Orientation Building & Reflection House | 2024-01-15 | 2024-05-12 | 5 months | Sole Source |  | FIDIC Yellow Book
7 |  | Establishment of CATT Fleet |  | Acquisition of 25 seater vehicles for child transport
8 |  | CSC South Work Package No2 |  | Enhancement of security infrastructure at the facility, aligned with TTPS, TTFS & Public Health recommendations | 2023-12-22 | 2024-04-30 | 4 months | Competitive Bidding |  | CATT SFC
9 |  | FireProof Filing Cabinets Kazim Towers (Port of Spain) |  | The purchasing of FireProof filing cabinets for CATT's Legal, Finance & HR Department | 2023-11-29 | 2024-03-30 | 2 months | Competitive Bidding |  | CATT SFC
10 |  | Medical Supplies for Mt Hope Assessment Centre |  | Medical Supplies and consumables for the daily operations of the Mt Hope Assessment Sentre | 2023-11-29 | 2024-02-28 | 2 months | Competitive Bidding |  | CATT SFC
11 |  | Annual Inspection of Fire Suppression System (Central) |  | Inspection, Service & Certification as per J.R. 3461 Kidde ECS FM-200 Fire suppression system | 2023-11-21 | 2024-03-30 | 2 months | Competitive Bidding |  | CATT SFC
12 |  | HSSE Items (To outfit centres with relevant HSSE Literature) |  | Establishment of permanent "HSSE Corners" at each facility | 2023-11-21 | 2024-03-30 | 1 month | Competitive Bidding |  | CATT SFC
13 |  | Inspection and Certification of Fire Extinguishers at 9 CATT Locations & Service of Fire Shield Fire Alarm System at 2 locations |  | Maintenance of Fire Suppression Equipments & Systems | 2023-11-22 | 2024-03-30 | 2 Months | Competitive Bidding |  | CATT SFC